## W1
PROJECT REPORT
Group | Group 5
Week | 04/01/2022 - 08/01/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Chooses project topic | Completed | Team come to an agreement of which topic should team choose for project
2 | Kicks off meeting | Completed | Meet up with team members
3 | Determine role of team members | Completed | Decide skills and strengths of each team member
5 | Analyze project requirements | Completed | Research information and rely on actual figures to predict usage needs
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Decides team rules and regulations | All Team | Sets out working rules and regulation upon agreements of everyone
2 | Brainstorm project ideas | All Team | Finds idea for project
3 | Brainstorm project ideas with the Instructor | All Team + Instructor(DuongTB) | Rules out which are good ideas and which are not
4 | Choose final project idea | All Team + Instructor(DuongTB) | Chooses final project idead
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Start planning for the web application project | 2022-01-15
2 | Start to design and make report | 2022-01-15
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W2
PROJECT REPORT
Group | Group 5
Week | 10/01/2022 - 15/01/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Make project requirements | In Progress | Discussion from the info based on the actual needs of those involved in the isolation process
2 | Define coding language | Completed | Use java language
3 | Design function model for web application | Completed | Finish the ERD diagram and database
4 | Build Entity Relationship Diagram and database | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Team meeting and make the plan | All Team | Finish the plan for this week, set the deadline for team member
2 | Discuss and list requirements | All Team | Define specific requirements for each user object.
3 | Create ERD Diagram and Database | All Team | Discuss and choose the final database
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
Design screen function
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W3
PROJECT REPORT
Group | Group 5
Week | 17/01/2022 - 21/01/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Build screen function | In Progress
2 | Finish ERD diagram | In Progress
3 | Finish database | In Progress
4 | Finish screen flow | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Team meeting and discuss | All Team | Finish the plan for this week, complete screen flow and ERD diagram
2 | Brainstorm project database with the Instructor | All Team + Instructor(DuongTB) | Discuss and choose the final version ERD, database
3 | Team meeting and continue editing ERD, database | All Team
4 | Create screen function | All Team | Team meeting every night(at least 2h) and discuss for screen function
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Start coding (front-end) | 2022-02-07
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W4
PROJECT REPORT
Group | Group 5
Week | 07/02/2022 - 11/02/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete ERD and Database, approved by the instructor | Completed
2 | Complete screen function | Completed
3 | Start building the front-end | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Team meeting and discuss | All Team | Warm up after Tet holiday, learn how to use git
2 | Brainstorm project database with the Instructor | All Team + Instructor(DuongTB) | Discuss and choose the final version ERD, database
3 | Team meeting and continue editing ERD, database and finish | All Team
4 | Start building the front-end | All Team | Team meeting every night(at least 2h) and code together
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Divide tasks, each member is in charge of a function and starts to code | 2022-02-17 | Start coding user functions (Register/login/Edit account information)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W5
PROJECT REPORT
Group | Group 5
Week | 14/02/2022 - 18/02/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code common function | Completed
2 |  | Completed
3 |  | Completed
4 |  | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1
2
3
4
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W6
PROJECT REPORT
Group | Group 5
Week | 21/02/2022 - 25/02/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code common function | Completed
2 |  | Completed
3 |  | Completed
4 |  | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1
2
3
4
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W7
PROJECT REPORT
Group | Group 5
Week | 28/02/2022 - 04/03/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Code common function | Completed
2 |  | Completed
3 |  | Completed
4 |  | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1
2
3
4
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes